## Slide 1: LV618 4G_5G migration internal kick-off Jun 10, 2025

## Slide 2
Goals
Project Goals – Benefit KDDI's business and operational objectives through the 4G/5G SDM Migration - Ph2 LV618 project. The final goal is 4G/5G migration by LV623.
Critical Success Factors – successful migration, deployment of 5G SDM network functions without service interruption.
Pressing milestones –
- LV618A Target Acceptance Dates: End of October 2025 and End of April 2026.
- LV618B Target Acceptance Dates: End of October 2025 and End of April 2026.
Project Context and Background – Customer & Nokia
Nokia
Overall TCO : 1 years of implementation + 1 year of Care
Any LDs/Penalties triggers: Yes
Other Key Partners
Customer Partners – Dell for HW, RedHat for OCP
Nokia Partners – Infinite, Wipro
MS Partner – N/A
Other BGs involved – N/A

## Slide 3
HW
  Products – N/A
  Vendor & BOQ – N/A
  Standard / PSI – N/A
  Forecast status & Lead time – N/A
Software
CNS
Products & Versions – Later slide
Compatibility Matrix – Later slide
  Pre-C3s: Deal breakers – Committed.
  S/W & Licenses BOQ - LV618AB_KDDI_24.JP.375003.01_NPT 75.0.0_5G-SDM_Migration_4G-SDM_re-installation_5G-SDM_PCF_system_installation.xlsb
Scope – HW, SW & Services – Nokia and any 3rd Party

## Slide 4
1. Project Overview

## Slide 5
Requirements Building the following nodes on the KDDI Common Virtualization Infrastructure (KYANOS)
Overall HLD LV553-C
AUSF/UDM LV618A
SCPv/BSF/DRA LV618A
PCFv/PCRFv LV618A
Mirroing Server LV618A
4G/5G Integrated EIR LV618A
4G/5G Integrated HSS/HLR LV618B
Project name
PO#102001124500 - LV 553 -C _ 5 GCSA _ Next Expansion and SDM Migration on KYANOS (Build) PO#102001302455 - LV618A_5GCSA_5G-SDM Integrated Migration on KYANOS PO#102001298117 - LV618B_5G-SDM Migration _ Integrated HSS Build
Completion Date April 2026
1. Project Overview

## Slide 6
2.Project Scope

## Slide 7
 | Work description | Comments​ |  | NOKIA | Dear KDDI Dear xGN
1) 5G-SDM Construction |  |  |  |  | 
 | 5G-SDM Construction | 4G/5G EIR (rebuild), HSS/HLR (rebuild), AUSF/UDM, SCP/BSF/DRA (SCPv), PCF/PCRFv, Mirroring Server V, NCOMv (new) | 4G/5G EIR (rebuild), HSS/HLR (rebuild), AUSF/UDM, SCP/BSF/DRA (SCPv), PCF/PCRFv, Mirroring Server V, NCOMv (new) | R | S
2) Integration with existing |  |  |  |  | 
 | NZEv, Custom Server v | NZEv and Custom Server V are the only existing integrations. (The new integration is in the Scope, while the other existing integrations are in the LV623 Scope.) |  | R | S
Proposal Nok5Gsa-SL-5386-4 N_LV618AB_ Integrated SDM_5G-SDM Migration Proposal _20250319.pdf
Excerpt from our company Pre-Sales Proposal
2. Project Scope

## Slide 8
System expansion, migration, and upgrade in three phases
Phase0
4G-PCRF migration
vIMS accomodation
Phase2
Infrastructure resource expansion
Integrated system addition
5 GC migration
MGMT system migration (partial)
Phase3
4G/5G PCRF integration
Phase1
Integrated system construction
4G-SDM migration
MGMT system migration (partial)
System upgrade on HaaS (SDL, AUSF/UDM, HSS/HLR, PCF/PCRFv, SCP/BSF/DRA)
Scope range
Next slide shows scope by contract (LV number)
Excerpt from our company Pre-Sales Proposal
2. Project Scope

## Slide 9
 | 2024 |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  |  | 
 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
Existing 5GC HaaS side
5G-SDM Migration to KYANOS
Migration
Applicable NF/NE/System (Ph.2):
AUSF/UDM, 5GEIR/EIR (reconstruction), HSS/HLR (reconstruction), SCP/BSF/DRA, PCF/PCRFv, Mirroring Serv. V
Note)NF/NE/System: 4G/5G common / NF/System: 5G only/NE: 4G only (winding)
5G side ordered
5G side not ordered
4G side ordered
Legend:
4G side not ordered
CR for integration
Work for KDDI/xGN
Support for NOKIA
HaaS SDL ExP Upgrade (24.7)
Integration SDL ExP Upgrade (24.7)
4-6-1
4-6-2
NF Removal
NAC/NetAct Removal
5-3
5-4
AUSF/UDM New build
SCPv/BSF/DRA New build
PCFv/PCRFv New build
Mirroing Server New build
4G/5G integrated EIR rebuild
4G/5G integrated HSS/HLR rebuild
Build on KYANOS (breakdown)
LV603A/B
LV604
Not PO
LV607
Not PO
OAM migration
5-4
5G-SOGW Upgrade in Provisioning Migration
4G-SOGW Upgrade in Provisioning Migration
5-2-1
5-2-2
4-6-4
Version 2025/4/21
4G SO GW EIR IMEI Prefix Double Probi
/ Model information transfer stop (V/K-LAB verification/commercial application)
5G-SOGW eps area deleted/SDP upper limit value changed
LV633
August 2025 PO desired
*Proxy connection (Voice Migration Step3/Dia Migration Step3/MAP Migration Step3/SBI Migration Step6) and DB migration (Voice Migration Step6/Dia Migration Step9/MAP Migration Step8/SBI Migration Step9) are included.
V Lab build/test
KDDI Lab build/test
Commercial system build
4-6-3
Overall design HLD
LV618A/B
LV553-C
3-3
Signaling path changed at peer node(SBI, Diameter) for 5GC
[5GC-SDM→ Integrated SDM Migration]
Voice Migration
Diameter Migration
SBI Migration
5-2-5
5-2-7
5-2-3
MAP Migration
5-2-6
Proxy Connection (SDL-SDL) + DB Migration (*)
5-2-4
Provisioning Remaining Migration Preparation
5-2-1
LV623-A/B
PO Received April 30, 2025
Construction of maintenance environment
4-6-5
PCRFv TEG
Signaling path changed at peer node (Diameter) for 4G/5GC
Removal of NF
5-5
5-6
Project scope and node breakdown
2. Project Scope
Excerpt from our company Pre-Sales Proposal

## Slide 10
3. Solution Overview

## Slide 11
DRA
CSD
Assurance
NAC
■5GC Existing system built on HaaS
■4G/5G integration System built on KYANOS
■4G SDM existing system
ELK Search
Mirroring Serv. V
DB Search
Search Serv.
UDR
SDL
EMS
NetAct
B&R
ARC
Log, H/C
Cust. Serv.
Assurance
NAC
HSS HLR
5G-EIR
EIR
PCFv PCRFv
Registers HSS/HLR
One-EIR
NPC
One-EIR
GW-STP
IMS
AS
AMF MME
SMF SPGW
P-CSCF
EDR log
DB Search
SO/Prov.
CHFoff/Mediator/BSS-GW
NM
NWR
Search Serv.
5G-SOGW
vHSS vHLR
5G-EIR EIR
PCFv PCRFv
One-EIR
Registers HSS/HLR
NPC
PCFd PCRFd
NPC
CHFon OCS
NCC
Fulfillment
FO
LCM/Orch.
NCOM
UDR
SDL
UDR
HSS HLR
EIR
PCRFv
PDR
EDR log
EMS
One-EIR
PCS5000
One-NDS
CMS8200
NetAct
Log Server
Registers HSS/HLR
SCC-AS
DEA
NTAS
CSD
4G/NSA subscriber accommodation
PCFd PCRFd
OCS CHFon
NPC
NCC
EDR log
Log, H/C
CHFoff/Mediator
NMd
Cust. Serv.D
NWRd
EMS, B&R
NZEd
■NCC/NPC System built on KYANOS
■4G SDM System built on KYANOS
UDM AUSF
SO/Prov.
SOGW
ELK Search
Mirroring Serv.
ELK Search
Mirroring Serv. D
U-DRA
CSD
BSF
CNDRA
SCP
CSD
STP
telesys MACHi7
BSF
CNDRA
SCPv
CSD
SCPd
DRAd
CSD
CSD
4G/NSA subscriber accommodation
Registers AUSF/UDM
LCM/Orch.
NCOMd
vPCRF
vPDR
CSDs
NPCs
EDR log
Log, H/C
Mediator
NMv
Cust. Serv.V
NWRv
EMS, B&R
NZEv
LCM/Orch.
NCOMv
5GSA subscriber accommodation
cHDR
CSD
UDM AUSF
Registers AUSF/UDM
Ph.2 Restructuring Integrated facilities
Ph. 2 installed Integrated facilities
NOKIA installation system
NOKIA product (CNF)
NOKIA product (VNF/VM)
NOKIA product (BM)
Diameter
http/2
Others
New Build
Existing NF/NE
MAP
HDR
CMS8200
SCC-AS
DEA
NTAS
CSD
Route switching
Route switching
Route switching
Route switching
Route switching
DB Search
Search Serv.
ExP UPG
ExP UPG
LCM/Orch.
NCOMv
Scope Range
(Re) Build Only
Build Nodes and Connections
Existing
Excerpt from our company Pre-Sales Proposal
3. Overview
- Target Node

## Slide 12
- Integration Matrix
Product name | OCP version | SW version | Signaling Opposing device | Installer device | Construction method | MGMT Opposing device (existing) |  |  |  | 
 |  |  |  |  |  | FM/PM | CM | B&R | Log collection | Health Check
AUSF/UDM | 4.18 | 24.7 | Connection up to Lv618 build unit | NCOMv | New | NZEv | GUI/CLI | NZEv | CSv | CSv
HSS/HLR | 4.18 | 24.7 |  |  | Sengu |  |  |  |  | 
One-EIR(4G/5G) | 4.18 | 24.7 |  |  | Sengu (4G) New (5G) |  | CLI |  |  | 
SCPv (SCP/BSF/DRA) | 4.18 | 25.7 |  |  | New (SCP/BSF) Sengu (DRA) |  | GUI/CLI |  |  | 
PCF/PCRFv | 4.18 | 25.7 |  |  | New |  |  | CSv |  | 
NCOMv | 4.13 | 24 FP1 | Connection up to Lv618 build unit | NCOMv | New | NZEv | GUI | CSv | CSv | CSv
Mirroring Server | 4.18 | N/A | SCPv | N/A |  | N/A | N/A(CLI) |  | N/A | N/A
Integrating between Lv618 constructors is done Signaling counter-devices are assumed to have completed integs after construction and before commercial traffic starts flowing in. ➡ Consultation with xGN/KDDI is required.
*OCP version is assumed to be OCP4.18
*OCP version compatible with NCOM24 FP1 is 4.13
3N Updated
3. Solution Overview

## Slide 13
New (Rebuild) Nodes/Systems​ | Vender Lab​@Tama |  |  | KDDI Tama Lab​ |  |  | Commercial​ |  |  | 
 | V-1-1​ | V-1-2​ | V-1-3​ | A-1​ | B-1​ | C-1​ | East​ Tama​ | East​ Oyama​ | West​ Osaka​ | West​ Chiyo​
One-EIR | 〇 | 〇 |  | 〇 | 〇 |  | 〇 | 〇 | 〇 | 
HSS/HLR | 〇 | 〇 |  | 〇 | 〇 |  | 〇 x 2 | 〇 x 2 | 〇 x 2 | 〇 x 2
UDM-AUSF | ◯ | 〇 |  | ◯ | ◯ |  | 〇 x 2 | 〇 x 2 | 〇 x 2 | 〇 x 2
NPCv (3 site geo x 2) | 〇 | 〇 | 〇 | 〇 | 〇 | 〇 | 〇 | 〇 x 2 | 〇 x 2 | 〇
SCPv (3 site geo x 2) | 〇 | 〇 | 〇 | 〇 | 〇 | 〇 | 〇 | 〇 x 2 | 〇 x 2 | 〇
Mirroring Server | ◯ | 〇 |  | ◯ |  | ◯ | 〇 | 〇 | 〇 | 〇
NCOMv | 〇 | 〇 |  | 〇 |  | 〇 | 〇 |  | 〇 | 
existing equipment | Vender Lab​@Tama |  |  | KDDI Tama Lab​ |  |  | Commercial​ |  |  | 
 | V-1-1​ | V-1-2​ | V-1-3​ | A-1​ | B-1​ | C-1​ | East​ Tama​ | East​ Oyama​ | West​ Osaka​ | West​ Chiyo​
NZEv | 〇 | 〇 |  | 〇 |  | 〇 | 〇 | 〇 | 〇 | 〇
Custom Server V | ◯ | 〇 |  | ◯ |  | ◯ | 〇 | 〇 | 〇 | 〇
- Facilities to be built in lab and commercial environments
Excerpt from our company Pre-Sales Proposal
3. Solution Overview

## Slide 14
*OCP version is assumed to be OCP4.18
*OCP version compatible with NCOM24 FP1 is 4.13
3. Compatibility Matrix

## Slide 15
Key requirements, use cases for acceptance
  Functional requirements and use cases : N/A
  Non-functional Requirements –
    Target Capacity : refer to next slide
    Security, Operational, Automation : N/A
  Alarm + Performance management : NZEv
  GR / DR (Solution & Trigger) :
    Geo Redundancy : SCP_BSF, NPCv *refer to “Solution overview”
    Disaster recovery：NCOMv *refer to “Solution overview”
  Migration : N/A (Lv623 scope)
Logical Solution Architecture diagram including system building blocks and key interfaces : refer to “Overview”
Topology diagram : refer to “Overview”
Number of sites : refer to “Solution overview”
Committed PreC3 features with timelines. : N/A
Reference to SharePoint folder : LINK
Change Management : LINK
Key Requirements, Use Cases & Solution

## Slide 16
(実トラフィックベースの収容数)
5GSA契約Sub想定収容数
⇒ SA6000万収容
Non-functional Requirements – Subscriber capacity requirement
多摩
小山
大阪
千代
多摩
小山
大阪
千代
既存HaaS
KYANOS
SDL21.2 ⇒21.8 ⇒22.8(VNF)
1600万収容
AUSF/UDM21.8⇒23.8
1080万収容
HSS/HLR21.8(VNF) ⇒23.8(CNF)
1080万収容
One-EIR21.5(VNF)
One-EIR21.8(CNF)
1080万収容
5G-CSD21.8(CNF) ⇒23.8
1080万収容
NPC21.8(VNF)⇒23.8
1080万収容
AUSF/UDM24.7(CNF)
SA2400万収容
HSS/HLR23.8(CNF)
5400万+SA1200万収
One-EIR24.7(CNF)
54M+SA12M subs
SDL22.8(CNF)
5400万+SA1800万収容 4500万+SA2300万収容
4G-CSD21.2(VNF)
5380万収容
4G SDM仮想化
+5GC KYANOS移行
注1) ‘5400万’は、4G SDM収容想定加入者数 注2) ’SA1200万‘は、初期5GSA収容想定加入者数
【既存1080万加入収容上限】
5G-CSD23.8(CNF)
5400万+SA1200万収容 ⇒ SA6000万収容
cHDRは途中増設が困難なため、初期構築時から最終収容想定容量で構築致します。
⇒ SA60M subs
Ph.3(以降)で、SA6000万加入収容対応に向けたCNF増設の想定です。
Ph.3(以降)で、SA6000万加入収容対応に向けてCNF増設の想定です。
4G/5G-EIR(コンボ)導入のため、再構築による増設･アップグレードを実施。
NPC25.7(CNF)
54M＋SA12M subs ⇒ SA60M subs
PCFv/PCRFvは途中増設が困難なため、初期構築時から最終収容想定容量で構築致します。
5G-CSD25.7(CNF)
54M+SA12M subs ⇒ SA60M subs
SCPは途中増設が困難なため、初期構築時から最終収容想定容量で構築致します。
Phase1拡張：～10月’25年
Phase2拡張：～12月’26年
Phase3拡張：12月’26年～
HSS/HLR 12.0M (xx.xxM)
4G/5G-EIR 12.0M (60M)
SCPv/BSF/DRA 12.0M (xx.xxM)
PCFv/PCRFv 12.0M (xx.xxM)
cHDR 12.0M (xx.xxM)
UDR 23.0M (23.0M)
AUSF/UDM 24.0M (xx.xxM)
HSS/HLR24.7(CNF)
54M+SA12M subs
EIR同一クラスタ再構築による増設･アップグレードを実施。
7N 更新
618B
618A
Out of scope
Out of scope

## Slide 17
SCD Local
MS E2E
LV618 project organization chart
PGM
Ikawa
Lead PM/TPM Muto
E2E SA Hirano Bala (OCP)
E2E TM Inoue
IP design Team Yukumoto
WAR Odanaka
KDDI CDL Aoki
CI OCP Certificate Rajalakshmi
MS
SCD Central
AUSF/UDM
PM Yokota
AUSF/UDM
SA/TM
Hisashi Ota
(Inoue)
TDL
AUSF/UDM SA Anadi
Engineer Lead
Engineer team
HSS/HLR
PM Umeda
HSS/HLR
SA/TM
TDL
HSS/HLR SA Anadi
Engineer Lead
Engineer team
SCPv/Mirroring Server
PM Ariuna
SCPv SA/TM Kakuta
(Sakaguchi/Yong)
TDL
SCPv SA Vipin/yadav
Engineer Lead
Engineer team
PCF/PCRFv
PM Natsume
PCF/PCRFv
SA/TM TBD
TDL Sushil
SA/TM Rahul 26/Mayank Joshi
Engineer Lead
Engineer team
NCOM
PM Fukuhara
TDL Yi-Chen
NCOM SA/TM Md Monirul Islam /Hashitani
Engineer Lead
Engineer team
5G-EIR/EIR
PM Umeda
5G-EIR/EIR
SA/TM
TDL
5G-EIR SA Ayan
Engineer Lead
Engineer team
CI
CI
MS
Mirroring Server SA/TM Open
Engineer
Lead
Engineer team
These nodes are managed by KDDI 認証Core department and VoLTE PGM Umeda-san manage those nodes.
TDL Rahul.12.Kumar (E2E)
Notes: あまり知られていない、パワーポイントで効率的に組織図を作る方法 [PowerPoint小技・小ネタテクニック]

## Slide 18
Project Plan & Critical Path
LV618A
LV618B
LV618A
LV618A
LV618A
LV618A
LV618B
Now

## Slide 19
Acceptance Criteria
■Acceptance 1: Assumed October 2025
Conditions: The work up to 10 in 2025 must be completed, and the deliverables of 1, 2, 3, 5, 7, 9, 10, and 12 on the previous page (initial version) must be presented.
■Acceptance 2: Assumed April 2026
Conditions: The work scheduled to be completed by April 2026 must be completed, and the deliverables of 13 and 24 on the previous page (initial version) must be presented.
■Acceptance 1: Assumed October 2025
Conditions: The work scheduled to be completed by 10 in 2025 must be completed, and the deliverables of 1, 2, 3, 5, 7, 9, 10, and 12 on the previous page (initial version) must be presented.
■Acceptance 2: Assumed April 2026
Conditions: The work scheduled to be completed by April 2026 must be completed, and the deliverables of 13 and 24 on the previous page (initial version) must be presented.
LV618A
LV618B

## Slide 20
Deliverables list
# | Document Name | Content and purpose | Language | Regional BWA
1 | HLD | - Basic design documents, Interface specifications, etc./- System Overview / Call Sequence Diagram | English | Yes
2 | LLD | - Detailed design documents, Parameter lists, etc. - System configuration files, etc. - System parameter management method - Equipment management - Lists of commercial settings corresponding to equipment ordered by buyer (Per equipment). | English | Yes
3 | Verification Test Plan | Including Verification Test Environment, Test scenarios and Test cases List, Schedule , Reporting | English | Yes
4 | IOT Test Plan | Same as the above | English | N/A
5 | Verification Test Report | Verification results. However, if the acceptance criteria for the software is met but there are remaining problems, provide the details of the problems, their impacts, workarounds and restrictions. | English | Yes
6 | IOT Test Report | Same as the above | English | N/A
7 | Software Release Note | Specify versions of soft wares, release dates, and the purpose(*) of release *Added features, fixed issues, and remaining issues | English | N/A
8 | Capacity Expansion Procedure | This procedure shall clearly state methods of sanity check of target devices, capacity expansion and methods for sanity check of target devices after the expansion. | English | N/A
9 | Alarm Manual | - Alarm list/- Alarm handling manual Actions for each alarm to be taken in operation when the alarm is generated to be specified. Manual for Troubleshooting. | English | N/A
10 | PM Counter Manual | Statistics list | English | N/A
11 | Instruction manuals | Instruction manuals for supplied equipments (Per equipment). | English | N/A
12 | O&M Manual | - Redundancy switching method/- Methods of sanity check of each equipment | English | N/A
13 | MOP | Procedures for Adding, Changing, and Deleting Settings | English | Yes
14 | Command Manual | - Command manuals/Documents showing examples of command usages and outputs. For procedures, both CLI and GUI procedures should be created. | English | N/A
15 | Software management | Software management method | English | N/A
16 | System Expansion Guidelines | Facility expansion work standard | English | N/A
17 | Document for pre-construction of commercial environment | Meeting materials for construction work commencement | English | N/A
18 | Verification environment management document | Documents related to Toyosu Lab environment construction(construction meeting document, construction completion document, list of settings) | English | N/A
19 | FOA Plan | (1) Test results of Nokia internal test (2) FOA Procedure (Should be confirmed in the vendor test environment in advance.) (3) FOA Schedule (It is expected to last about two weeks.) (4) FOA operation and communication system table (5) List of sanity check items during FOA period (6) FOA Acceptance Criteria Statement | English | N/A
20 | FOA Report | (1) Report of sanity check results during FOA period | English | N/A
21 | OJT material | ・Simplified version of operation manuals. ・Items to be included in OJT material will be discussed separately. ・List of Commercial Settings (Including setting values of system parameters that are independent from the service to be accommodated and the reasons.) | English | N/A
22 | Maintenance Agreement (Confirmation document) | (1) Maintenance operation flow (2) Maintenance SOW (3) Supplier Maintenance Operation Communication System | English | N/A
23 | Site test report | Verification results of acceptance tests conducted at commercial equipment construction. | English | N/A
24 | Commercial work completion report | This document will be submitted after CRO is completed. | English | Yes

## Slide 21
Cost Baseline
PTA Template V.2.0_2023 CNS GBC Japan
LV618A
LV618B

## Slide 22
Cost Baseline
Revenue, Cost, Risk Cost, Target SM% per Product Line/GIC
WtD-G5-BusinessCase
OEM -> SM 30%
Services -> 36% SM
Global SM = 35.6%
Please see WtD G5 Link:
ServiceCost:
40_Service_Cost

## Slide 23
# | Dependency | Immediate Milestone Impacted | Need By Date | Team | Owner Name | On Critical Path? | Impact of Delay
1 | CaaS OCP cluster ready for each environment | Refer to slide 20 “Project Plan & Critical Path” |  | xGN | Takagishi | Yes | NCOM deploy delay at V lab
2 | NOKIA V-lab NCOM ready for NF installation |  |  | NOKIA | Fukuhara | Yes | NF deploy delay at V lab
Key Dependencies
List high priority dependencies on Customer, 3Ps, R&D, other BGs:

## Slide 24
Risk Items | Background and Description | Risk Avoidance Measures | When to Apply
Disk Performance Problems (Performance Test) | Disc performance-related measures have occurred in the JCOM PJ | Based on information sharing from PJs that have already been executed, measures are applied during construction and verification in this PJ (Consider when creating LLDs) | During lab construction and verification JCOM: #24175 VOLTE: QA#5430, QA#5462
Delay in lab construction | CNF on-board delay to KYANOS | Obtain information such as problem occurrence event and solution from the executed PJ (JCOM) and apply it to the construction work | During lab construction and commercial construction
Problem leakage due to lack of consideration of the test scope | Failure to prevent problem leakage due to insufficient test scope | After examining the necessary background call type and SO type, item review was conducted from the viewpoint of ensuring the completeness of the test scope | When developing the test plan At the time of verification
Leakage of KPI problem | 5 At GC Ph1, JCOM PJ, problem was leaked because KPI check was omitted. | In performance test and long-term stability test, check from the viewpoint of whether statistical information can be correctly measured by the equipment under evaluation and the EMS side. | When creating KPI verification items 5GC Ph1:#20099 JCOM PJ:#28306
Risk management
The following measures should be taken together from the review of past cases.
Since there are a wide range of departments related to infrastructure vendors, KDDI, xGN, and our company, we will promote PJ by closely sharing external and internal information.

## Slide 25
Risk Items | Background and Description | Risk Avoidance Measures | Time of application
Lack of consideration of commercial environment | Lack of consideration of call processing type that actually occurs in operation caused an assumed event when commercial work is performed | Background Examination of call type | During test planning
Misunderstanding of work schedule (method) | When the connection with OAM equipment is integrated with commercial equipment: An omission in consideration was discovered at the time of work approval. | Agreement on verification items before the procedure verification/rehearsal Commercial work procedure establishment completed before XX | ・At the time of procedure examination ・At the time of procedure examination
Unexpected event occurred in commercial work | When the connection with the OAM equipment is integrated with the commercial equipment: The commercial configuration and SW operating conditions were not considered at the time of procedure examination | At the time of procedure examination, the actual working time period was considered, and the conflict with the periodic processing was confirmed, and the validity of the work execution order was confirmed. | At the time of design implementation
Risk management

## Slide 26
Communication/Conference Management
.
Conference Information | Schedule | Implementation Time | Participant | Agenda Contents | Adjustment Method | Operation method
Regular project (KDDI Data Core Technology Department, xGN Administration Node) | Scheduled | Every Friday 11:00~12:00 | xGN/NOKIA | Progress, issues, and risk sharing | 〃 | 〃
[Existing] Middle Meeting | Held regularly | Every other Wednesday 17:30-18:30 | KDDI General Manager/xGN General Manager/NOKIA CDL/NOKIA | Sharing progress, issues, and risks at the middle level | 〃 | 〃
[Existing] General Manager's Meeting General Manager's Meeting | Regular meeting | Once a month (set each time) | General Manager, General Manager, KDDI Division/NOKIA CDM | High-level sharing of progress, issues, and risks | Coordinating the next meeting during the meeting | 〃
Customer Meeting
Internal Meeting
Conference Information | Schedule | Implementation Time | Participant | Agenda Contents | Adjustment Method | Operation method
Internal Project sync-up meeting (Overall) | Scheduled | (TBD) Every Tuesday 14:00~15:00 | NOKIA project key members | Progress, issues, and risk sharing | 〃 | 〃
Notes: Regular overall
Schedule needs to be adjusted
xx:xx~xx:xx
KDDI/xGN/NOKIA
Overall progress, issues, and risk sharing
Regular
Conference call
Report and discussion based on data

## Slide 27
Nokiamine (Ticket tool) : LINK
Project Repository, Tools & Access
Project Repository:
PDR directory where all project documents will be stored and maintained : LINK
PMAT ID and link : MP1000065
including presales documents for Handover : Refer to PTA document
Project Tools:
Sales force (Ticket tool for Delivery/L3)
JIRA (Ticket tool for RnD)
Business planner tool (Resource request, Demand)
Project tool (Finance management)
Customer Tools & Access
Nokia Tools & Access

## Slide 28
Project Readiness Assessment (PRA) Actions & Status
Item # | Action | Category | Owner | Issue Date | Deadline | Closed Date | Status | Remarks
1 | PTA |  |  |  |  |  |  | 
2 |  |  |  |  |  |  |  | 
Exec Summary
This opportunity (628) is 100% and PO expected early May. Scope: logical next step of integration and migration after CNF build and onboarding scope on KYANOS (618) whose execution has commenced. Migration strategy can be reused from other projects. Technically, solution is complex but familiar, and major risk is resourcing.
Key Points & Actions
1. TCO is only delivery (May to July ’27) . Care scope will be separate. No upgrade planned during project. No HW, SW – only services.
2. Solution is migration of SDL (VNF) to combined 4G and 5G SDL (CNF)
3. CNF versions will be 24.7 / 25.7.
4. Pre-C3s: 2 x Deal breakers – committed.
5. Total ~70M subs – 4G 45M 5G 24M; 55M subs will be migrated as part of other projects such as VOLTE. 623 will involve migration of 15M 5G subscribers
6. Migration – no separate tool will be used. As used in other projects, SDL Proxy Migration Feature will be used.
7. No security requirements. Perf testing will be performed by customer
8. Tests for acceptance – existing 4G/5G services.
9. Services :
a. Onsite and offsite resources used to cater for onsite JP speaking resources and MOPs in Japanese for KDDI to cater for this very complex program
b. Issue : Resource issue flagged for both market and domains which is heavily impacting 618 and now also a heavy risk for 623
c. Forecast resources required in the system - @Kunio Ikawa (Nokia) @Rahul 12. Kumar (Nokia) @Yi-Chen Chiu (Nokia) @Carlos Gonzalez de Requena Farr (Nokia)
10. Migration – 2M duration taken . strategy from existing projects to be reused
11. Standard TSD & SSD not used – review the ppt and feedback on key contractual clauses to be incorporated in the slide pack - @ThienMing Foo (Nokia)
Project Readiness Assessment (PRA) Actions has been completed.

## Slide 29
Next 20-day plan and deliverables
Key Actions
# | Action | Owner | Date
1 | Internal project kickoff | Ikawa | 6/9
2 | HLD / v lab LLD design start | Each NF SA | Design fixed target : 7/25
3 | Project preparation (WBS, SvO, PJ tool, PMAT) | MS : Muto SSP : Rahul, Sushil CI : Yi-chen | TBU
Key Deliverables
# | Deliverable | Owner | Date
1 | HLD | Each NF SA | Design fixed target : 7/25
2 | V lab LLD | Each NF SA | Design fixed target : 7/25

## Slide 31
Agenda
Project Context and Background – Customer & Nokia
Scope – HW, SW & Services – Nokia and any 3rd Party
Key Requirements, Use Cases and Solution
Project Organisation
Project Plan and Critical Path
Acceptance Process
Milestone Table – Milestones , Criteria, Payment & Revenue recognition
Share of Responsibility – Customer vs Nokia, Nokia Internal, Nokia vs Supplier
Cost Baseline
Key Document Deliverables
3rd Party Scope & Milestone
Logistics for HW Shipment
Key Dependencies
Key Risks
Stakeholders, Communication and Governance Plan – Customer, Internal and 3rd Party
Project Repository, Tools & Access
Project Readiness Assessment (PRA) Actions & Status
Next 20-day plan

## Slide 32
Audience – Kick Off | Organized by PEO (BGDM or Customer PM)
Account Manager
Sales Leader
Presales Solution and Services Managers
Product Line Manager
Business Group Delivery Manager
Project Director
Lead Architect
Project Contract Manager
Legal (optional - if applicable/required)
Market Operations and Procurement
Commercial/Pricing Manager
Project team members – PM, SA, TPM, TDL, DA, others involved to date
Customer Care Manager (optional - if applicable/required)
Domain Delivery Lead
Market PMO Manager
Project Financial Controller
Cost & Progress Manager
Customer PM MUST ensure that TRICORN roles are covered
Tricorn Model (sharepoint.com)

## Slide 33
# | Category | Risk description | Impacted immediate milestone | Impact Quantum | Treatment – Mitigate / accept/transfer | Risk actions | Owner | Key Contri to mitigate
1 |  |  |  |  |  |  |  | 
2 |  |  |  |  |  |  |  | 
3 |  |  |  |  |  |  |  | 
4 |  |  |  |  |  |  |  | 
5 |  |  |  |  |  |  |  | 
Key Risks
Top 5 prioritized risks with high probability and high impact ($$ and customer):
Do incorporate the risks identified in presales phase.
Risk Management
Every month, plan internal and customer risk management sessions to look at risks of immediate milestones and any major ones for the rest of the program
Risk register will be maintained
Kickoff資料参照

## Slide 34
Comms Type | Stakeholders | Type | Artefact - Owner | Frequency /date | Owner
Weekly Project | Nokia & customer project team | meeting | Weekly Project Status Report -PM | e.g. weekly/ Wednesday | PM
Fortnightly Governance | Nokia: Customer | meeting | Governance Pack - PD | Every 2nd week - Friday | PD
Monthly Steering Co. | Nokia: Customer | meeting | Steering Co Pack - BGDM | Every month – 15th | AM
Stakeholders, Communication & Governance – Customer & Internal
Key Customer Stakeholders
Name | Team | Role & Designation
Key Nokia Stakeholders
Name | Team | Role & Designation
Customer Meeting & Governance
Comms Type | Stakeholders | Type | Artefact - Owner | Frequency /date | Owner
Weekly Project | Nokia project team | meeting | Internal weekly Project Status Report -PM | e.g. weekly/ Wednesday | PM
Internal Sales/Delivery Governance | PM, TDL, SA | meeting | Internal Governance Pack - PD | Every 2nd week - Friday | PD
Internal Delivery Governance | Nokia: Customer | meeting | Internal Steering Co Pack - BGDM | Every month – 15th | AM
Internal Meeting & Governance

## Slide 35
SoR – Customer vs Nokia, Nokia Internal, Nokia vs Supplier
Activity | Customer | Nokia
Activity | R | S
Customer & Nokia SOR
Activity | Nokia | 3P
Activity | R | S
Nokia & 3P SOR
Activity | CNS | MN | NI
Activity | R | S | 
Internal Nokia SOR
Mention the critical , complex scenarios often with grey areas for which we’ll need clarity prior and present here : e.g.: HW delivery, site readiness, cloud install